## Sheet1
Sr. No | JV Name | Phase | Scheme No. | District | Taluka | Grampanchayat | Village / Habitation | Proposed ECU Capacity (gms/hr) | No. of EC Unit | Nos. of Proposed Switch Room | Work Order No | Cost of EC Unit as per WO | Cost of EC Room as per WO | Cost of Comp Maint as per WO | Work Order Cost (EC unit+EC Room+Comp Maint) Without GST | Date of Work Order | Work Order End Date | WO (5%) Billing Date | 5% Scan Uploading | WO (5%) Amount | Date of Supply | Nos. of EC Unit Supplied | Supply (60%) Billing Date | 60% Scan Uploading | Supply (60%) Amount | Date of Installation | Nos. of EC Unit Installed | Installation (25%) Billing Date | 25% Scan Uploading | Installation (25%) Amount | Date of Commisioning | Nos. of EC Unit Commisioned | Date of TPI Inspection | Test Report Received Date | Commisioning (10%) Billing Date | 10% Scan Uploading | Commisioning (10%) Amount | EC Room (Yes/NO) | Date of EC Room Completion | EC Room Completion Status | EC Room Bill Date | Remark with Date | EC Room Constructed (Yes/No) | NOC Received | Power Supply issue | EC Room Cancelled | Operation & Maintenance commenced date
1 | SMC JV | I | 6999 | Kolhapur | Ajara | Gajargaon | Gajargaon | 50 | 1 | 0 | SWSM / JJM/ EC/CR- 168/ W.O./ Kolhapur /343/2023 | 310154.1687 | 0 | 93046.4 | 403200.5687 | 2023-03-08 | 2023-11-05 | 18-04-2023 | Uploaded | 15507.7084 | 2023-06-06 | 1 | 21-12-2023 | Uploaded | 186092.5012 | 2023-09-01 | 1 | 2024-06-08 | Uploaded | 77538.5422 | 2023-09-01 | 1 |  | 2023-12-01 |  |  | 31015.4169 | No |  | NA |  |  |  | Yes |  |  | 2023-09-02
2 | SMC JV | I | 7018 | Kolhapur | Ajara | Maligre | Maligre | 50 | 1 | 0 | SWSM / JJM/ EC/CR- 168/ W.O./ Kolhapur /343/2023 | 310154.1687 | 0 | 93046.4 | 403200.5687 | 2023-03-08 | 2023-11-05 | 18-04-2023 | Uploaded | 15507.7084 | 2023-06-06 | 1 | 21-12-2023 | Uploaded | 186092.5012 | 2023-09-01 | 1 | 2024-06-08 | Uploaded | 77538.5422 | 2023-09-01 | 1 |  | 2023-12-01 |  |  | 31015.4169 | No |  | NA |  |  |  | Yes |  |  | 2023-09-02
3 | SMC JV | I | 7028 | Kolhapur | Ajara | Sarambalwadi | Sarambalwadi | 25 | 1 | 0 | SWSM / JJM/ EC/CR- 168/ W.O./ Kolhapur /343/2023 | 209356.7559 | 0 | 62807 | 272163.7559 | 2023-03-08 | 2023-11-05 | 18-04-2023 | Uploaded | 10467.8378 | 2023-04-07 | 1 | 14-07-2023 | Uploaded | 125614.0535 | 18-04-2023 | 1 | 2024-06-08 | Uploaded | 52339.189 | 18-04-2023 | 1 |  |  |  |  | 20935.6756 | No |  | NA |  |  |  | Yes |  |  | 2023-04-19
4 | SMC JV | I | 7220 | Kolhapur | Karveer | Nitavade | Nitavade | 25 | 1 | 0 | SWSM / JJM/ EC/CR- 168/ W.O./ Kolhapur /343/2023 | 209356.7559 | 0 | 62807 | 272163.7559 | 2023-03-08 | 2023-11-05 | 18-04-2023 | Uploaded | 10467.8378 | 2023-04-07 | 1 | 14-07-2023 | Uploaded | 125614.0535 |  |  |  |  | 52339.189 | [6 empty] | 20935.6756 | No |  | NA | [6 empty] | 1899-12-31
5 | SMC JV | I | 7227 | Kolhapur | Karveer | Patekarwadi | Patekarwadi | 25 | 1 | 0 | SWSM / JJM/ EC/CR- 168/ W.O./ Kolhapur /343/2023 | 209356.7559 | 0 | 62807 | 272163.7559 | 2023-03-08 | 2023-11-05 | 18-04-2023 | Uploaded | 10467.8378 | [9 empty] | 52339.189 | [6 empty] | 20935.6756 | No |  | NA | [6 empty] | 1899-12-31
6 | SMC JV | I | 7299 | Kolhapur | Shirol | Kanwad | Kanwad | 100 | 1 | 0 | WO Not Received/Rejected by department as per letter |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 | [6 empty] | 0 |  |  | NA | [6 empty] | 1899-12-31
Formulas:
Work Order End Date = [Date of Work Order]+242
Operation & Maintenance commenced date = [Date of Installation]+1

## Sheet2
District | Taluka | Grampanchayat | Village / Habitation | Proposed ECU Capacity (gms/hr)

## Sheet3
Region | Agency | Employe name | Email | Phone
Amravati | M/s Ceinsys | Rishikesh Salunke | salunkerishikesh@gmail.com | 9834955236
Nashik | M/s Ceinsys | Rishikesh Salunke | salunkerishikesh@gmail.com | 9834955237
Chhatrapati Sambhajinagar | M/s Rite water | Aniruddha Dhumale | aniruddhadhumale@gmail.com | 8995623147
Nagpur | M/s Rite water | Aniruddha Dhumale | aniruddhadhumale@gmail.com | 8995623148
Konkan | M/s Indo | Rishikesh Salunke | rushikeshsalunkhe33@gmail.com | 9834955236
Pune | M/s Chetas | Rishikesh Salunke | rushikeshsalunkhe33@gmail.com | 9834955237